## A3 Summary
EK-2905 HYUNDAI BC3H BENZİN DEPO KAPAĞI KALIBI YÜKSEK FİRE PROBLEMİ PPS | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI | OTOMOTİV PPS / 8 ADIMLI A3 PROBLEM ÇÖZME FORMATI
VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ | VAKA BİLGİLERİ |  | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM | VAKA BİLGİLERİ — DEVAM
PPS ID | PPS-001 |  | Problem Başlığı | EK-2905 Kalıbı Yüksek Fire Oranı |  |  |  |  | Problem Lideri | Gökhan Özen |  |  | Müşteri / Tesis | T2 Tesisi |  | Hat / Makine | E-91 / 600T |  |  |  |  | Öncelik | Yüksek
Bölüm | Proses Geliştirme |  | Parça / Proses | BC3H Benzin Depo Kapağı (2305688) |  |  |  |  | Açılış Tarihi | 2026-08-01 |  |  | Revizyon | 0 |  | Hedef Kapanış | 2026-09-04 |  |  |  |  | Genel RAG | Kırmızı
ADIM 1 — PROBLEM TANIMI | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN | ADIM 1 — PROBLEMİ NETLEŞTİRİN |  | ADIM 4 — KÖK NEDEN ANALİZİ | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN | ADIM 4 — KÖK NEDENİ ANALİZ EDİN
ADIM 2 — PROBLEMİ PARÇALARA AYIRMA | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN | ADIM 2 — PROBLEMİ PARÇALARA AYIRIN
[13 empty] | ADIM 5 — UYGULAMA PLANI | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN | ADIM 5 — UYGULAMA PLANI YAPIN
[13 empty] | KN ID | KÖ ID | Karşı Önlem / Aksiyon |  |  |  | Etkisi | Maliyeti | Süresi | Öncelik Puanı | Sorumlu | Termin
[13 empty] | KN1-KN4 | KÖ1 | Mevcut lokma, daha yüksek mukavemetli çelikten yeniden üretilerek değiştirilecek ve önüne geçilecektir. |  |  |  | 5 | 4 | 4 | 80 | Ceyhun Benli | Week 36
[13 empty] | KN2 | KÖ2 | Parting line bölgesindeki açıların boya prosesine uygun hale getirilecek şekilde tasarım değişikliği ve kalıp modifikasyonu |  |  |  | 5 | 1 | 1 | 5 | Ürge | -
[13 empty] | KN3 | KÖ3 | Lokma yenilendikten sonra proses parametreleri optimize edilerek proses doğrulaması gerçekleştirilecektir. |  |  |  | 5 | 5 | 5 | 125 | Gökhan Özen | Week 34
Alt Problem |  |  |  |  | Etki | Öncelik | Kanıt / Kaynak
Çatlak Firesi |  |  |  |  | 60.88% | 1 | Kalite fire oranları pareto dokümanı | [5 empty] | ADIM 6 — ÇÖZÜMLERİ UYGULAMA | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN | ADIM 6 — ÇÖZÜMLERİ UYGULAYIN
Dur kalk Firesi |  |  |  |  | 17.49% | 2 | Kalite fire oranları pareto dokümanı | [5 empty] | Karşı Önlem ID |  | Aksiyon ID | Uygulama / tamamlanma kanıtı |  |  |  |  | Tarih |  | Sorun / Sapma
Setup Firesi |  |  |  |  | 6.76% | 3 | Kalite fire oranları pareto dokümanı
Serpme Firesi |  |  |  |  | 4.96% | 4 | Kalite fire oranları pareto dokümanı | [5 empty] | ADIM 7 — SONUÇLARI İZLEME | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN | ADIM 7 — SONUÇLARI İZLEYİN
ADIM 3 — HEDEF BELİRLEME | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN | ADIM 3 — HEDEF BELİRLEYİN |  | KPI | KPI | Önce | Önce | Hedef | Hedef | Sonra | Sonra | Sürdürme | Sürdürme | Sonuç | Sonuç
SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | SMART hedef ve beklenen durum | Başlangıç | Başlangıç | Hedef | Hedef |  | Fire Oranı |  | 16% |  | 3%
EK-2905 kalıbındaki fire oranını %3'ün altına düşürmek. | [7 empty] | Week 36 |  | <3%
[13 empty] | ADIM 8 — STANDARDİZASYON / KURUMSALLAŞTIRMA | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN | ADIM 8 — STANDARDİZE EDİN
[13 empty] | Standart / doküman | Standart / doküman | Standart / doküman | Standart / doküman | Güncellendi? | Güncellendi? | Sorumlu / tarih | Sorumlu / tarih | Sorumlu / tarih | Yatay yayılım / ders | Yatay yayılım / ders | Yatay yayılım / ders
Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı: | Hedef tarihi / takip sıklığı / veri kaynağı:
Hazırlayan | Sol taraf gözden geçiren | Sol taraf gözden geçiren | İmza |  | Tarih | Kontrol Eden | Karar | Karar | İmza |  | Tarih |  | Onaylayan | Sağ taraf gözden geçiren | Sağ taraf gözden geçiren | İmza |  | Tarih | Kapanış kararı | Kapanış kararı | Kapanış kararı | Onay | Onay | Onay
Gökhan Özen | [5 empty] | Barış Gövem
KN2
KN1
KN3
EK-2905 Kalıbında Yüksek Fire
Enjeksiyon Problemleri Nedeniyle
%16 Yüksek Fire Oranında
600T E-91 Enjeksiyon Makinesinde
15.07.2026
Enj. Makinesi Değişikliği ile
T2 Üretim Tesisi
İdeal Durum: 04.09.2026'dan itibaren
EK-2905 enjeksiyon fire oranının %3'ten düşük olması
Mevcut Durum: 15.07.2026'dan itibaren
EK-2905 enjeksiyon fire oranı ortalama %16,4
Problem Tanımı: İdeal durum ile mevcut durum arasında %13,4'lük bir sapma bulunmaktadır.
15 Temmuz sonrasında oluşan firelerin toplam maliyeti: Parça Birim Maliyeti : 63,34 TL Fire Edilen Parça Sayısı : 1.687 adet
FireMaliyeti (15.07/05.08) : 106.854,58 TL / 20 gün
Fire Maliyeti (2026) : 398.345,26 TL
Bu 4 hata modunun toplam firedeki oranı:
%90,11
Ortalama %16,4 fire oranının %14,8'i
2026 İlk 7 Aylık Kayıp
2.769 €
Kalıp alıştırma hattı deformasyon
ÇAPAK PROBLEMİ
(%1,36 Çapak Alma İşlemi Sonrası)
SERPME PROBLEMİ
(%4,96 fire oranı)
ÇATLAK PROBLEMİ
(%60,90 fire oranı)
Note on A7: Problemi gözlenebilir gerçeklerle yazın; Problemin net tanımı: Ne? Nerede? Ne zaman? Ne kadar? Müşteri / güvenlik / kalite / teslimat / maliyet etkisi nedir? Şüphelenilen nedenleri Adım 4 altında değerlendirin. Durumu inceleyin ve ana problemi açık, ölçülebilir ve neden varsaymadan ortaya koyun.
Note on A16: Büyük sorunu daha küçük, veriyle karşılaştırılabilir ve yönetilebilir alt parçalara bölün. Mevcut durumu gembada doğrulayın.
Note on N36: Süreci ve elde edilen sonuçları takip edin; hedef, önce/sonra ve sürdürülebilirlik verilerini karşılaştırın.
Note on A37: Ulaşılmak istenen somut, gerçekçi, zaman sınırlı hedefi; başlangıç değeri ve KPI tanımıyla birlikte belirleyin.
Note on N40: Başarılı sonucu standart hâle getirin, ilgili dokümanları güncelleyin ve yatay yayılım ile paylaşın.

## Problem Definition
PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION | PROBLEM DEFINITION
Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data. | Clarify the gap before analysing causes. Use facts from gemba and traceable data.
5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE | 5W2H / SCOPE
Field | Entry | Evidence / source
What
Where
When / frequency
Who affected
How many / magnitude
How much cost / risk
IS / IS NOT | IS / IS NOT | IS / IS NOT | IS / IS NOT | IS / IS NOT | IS / IS NOT | GEMBA OBSERVATION | GEMBA OBSERVATION | GEMBA OBSERVATION | GEMBA OBSERVATION | GEMBA OBSERVATION | GEMBA OBSERVATION
Dimension | IS | IS NOT | Boundary / implication
Product
Process step
Location
Time
Population
PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION | PROBLEM BREAKDOWN / PRIORITISATION
Segment | Measure | Baseline | Defects | Volume | Rate | Share | Priority | Selected? | Evidence | Owner | Notes
Product
Process
Shift
Machine
Supplier lot
Customer
Other
| Mevcut Durum (01.08.2026) | İdeal Durum (04.10.2026)
Fire Oranı (fire per Lot) | 16.4% | 3%
Hedeften Sapma %13,4

## Data Analysis
DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS | DATA ANALYSIS
Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table. | Enter chronological KPI observations. The chart updates from the table.
Date | KPI | Actual | Target | Unit | Phase | Product / Line | Source / Evidence | Defects | Volume | Rate | Comment
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline
| Primary KPI |  |  |  | Baseline

## Root Cause Analysis
ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS | ROOT CAUSE ANALYSIS
Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence. | Separate occurrence, escape/detection and systemic causes. Verify every selected root cause with evidence.
ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES | ISHIKAWA / CAUSE HYPOTHESES
Cause ID | Category | Potential cause | Occurrence / Escape / Systemic | Evidence for | Evidence against | Test method | Test owner | Due date | Result | Verification | Selected root? | Risk | Notes
C01 | Man |  | Occurrence | [6 empty] | Not Tested | No
C02 | Machine |  | Occurrence | [6 empty] | Not Tested | No
C03 | Method |  | Occurrence | [6 empty] | Not Tested | No
C04 | Material |  | Occurrence | [6 empty] | Not Tested | No
C05 | Measurement |  | Escape | [6 empty] | Not Tested | No
C06 | Environment |  | Systemic | [6 empty] | Not Tested | No
C07 | Management System |  | Systemic | [6 empty] | Not Tested | No
5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS | 5 WHY CHAINS
Chain | Cause type | Problem / starting point | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Root cause statement | Evidence | Can switch on/off? | Verification | Cause ID | Owner
W1 | Occurrence | [9 empty] | Not Tested
W2 | Escape | [9 empty] | Not Tested
W3 | Systemic | [9 empty] | Not Tested
W4 | Occurrence | [9 empty] | Not Tested
W5 | Escape | [9 empty] | Not Tested
W6 | Systemic | [9 empty] | Not Tested
W7 | Occurrence | [9 empty] | Not Tested
W8 | Escape | [9 empty] | Not Tested
ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL | ROOT CAUSE VERIFICATION & APPROVAL
Cause ID | Verified root cause | Type | Evidence summary | Reproduction / disconfirmation test | Result | Confidence % | Approver | Approval date | Decision | Linked action IDs | Residual uncertainty | Customer relevance | Notes
Draft
Draft
Draft
Draft
Draft

## Action Plan
ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER | ACTION PLAN & CONTAINMENT TRACKER
All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence. | All actions need a verified cause link, accountable owner, due date and objective completion evidence.
Action ID | Type | Action / countermeasure | Cause ID | Owner | Planned start | Due date | Actual finish | Status | Priority | Days late | RAG | Completion evidence | Effectiveness evidence | Customer approval | Notes
A01 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A02 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A03 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A04 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A05 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A06 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A07 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A08 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A09 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A10 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A11 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A12 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A13 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A14 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A15 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A16 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A17 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A18 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A19 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A20 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A21 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A22 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A23 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A24 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
A25 | Corrective | [6 empty] | Not Started | Medium | 0 | Green
Formulas:
ACTION PLAN & CONTAINMENT TRACKER = IF(OR([ACTION PLAN & CONTAINMENT TRACKER]="",[ACTION PLAN & CONTAINMENT TRACKER]="Complete",[ACTION PLAN & CONTAINMENT TRACKER]="Cancelled"),0,MAX(0,TODAY()-[ACTION PLAN & CONTAINMENT TRACKER]))
ACTION PLAN & CONTAINMENT TRACKER = IF([ACTION PLAN & CONTAINMENT TRACKER]="Complete","Green",IF([ACTION PLAN & CONTAINMENT TRACKER]="Blocked","Red",IF([ACTION PLAN & CONTAINMENT TRACKER]>0,"Red",IF(AND([ACTION PLAN & CONTAINMENT TRACKER]<>"",[ACTION PLAN & CONTAINMENT TRACKER]-TODAY()<=3),"Amber","Green"))))
Note on L3: [Yorum yazışması] Excel sürümünüz bu yorum yazışmasını okumanıza izin veriyor, ancak dosya daha yeni bir Excel sürümünde açılırsa, yapılan düzenlemeler kaldırılır. Daha fazla bilgi: https://go.microsoft.com/fwlink/?linkid=870924. Açıklama: RAG is formula-driven: blocked or overdue = Red; due within three days = Amber; otherwise Green; completed = Green.

## Effectiveness Check
EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK | EFFECTIVENESS CHECK
Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation. | Confirm that results are sustained, not merely improved immediately after implementation.
KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION | KPI VERIFICATION
KPI | Definition | Baseline | Target | Post-action | Sustain | Unit | Improvement % | Target met? | Verification window | Evidence URL / ref | Conclusion
Primary KPI
Secondary KPI 1
Secondary KPI 2
Customer escapes
Scrap / rework
Process capability
Detection effectiveness
Other
SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS | SUSTAINMENT AUDITS
Audit date | Area / line | Standard checked | Sample size | Conforming | Nonconforming | Compliance % | Auditor | Finding | Reaction action ID | Next audit | Status
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
KPI | Baseline | Target | Post-action | Sustain
Primary KPI | 0 | 0 | 0 | 0
Secondary KPI 1 | 0 | 0 | 0 | 0
Secondary KPI 2 | 0 | 0 | 0 | 0
Customer escapes | 0 | 0 | 0 | 0
Scrap / rework | 0 | 0 | 0 | 0

## Lessons Learned
STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED | STANDARDIZATION, YOKOTEN & LESSONS LEARNED
DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES | DOCUMENT / SYSTEM UPDATES
Item | Update required? | Document / system ID | Current revision | New revision | Owner | Due date | Completion date | Status | Approval | Evidence | Customer submission? | Notes
PFMEA | Yes | [6 empty] | Not Started | Draft
Control Plan | Yes | [6 empty] | Not Started | Draft
Work Instruction | Yes | [6 empty] | Not Started | Draft
Inspection Standard | No | [6 empty] | Not Started | Draft
Training / Competence | Yes | [6 empty] | Not Started | Draft
Layered Process Audit | No | [6 empty] | Not Started | Draft
APQP / PPAP record | No | [6 empty] | Not Started | Draft
HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN | HORIZONTAL DEPLOYMENT / YOKOTEN
Site / line / product | Applicability | Risk reviewed | Action required | Owner | Due date | Status | Completion evidence | Effectiveness checked | Check date | Result | Approval | Notes
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
[6 empty] | Not Started |  |  |  |  | Draft
LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE | LESSONS LEARNED & CLOSURE
What went well?
What failed or was delayed?
What evidence changed our thinking?
What should be reused?
What should be avoided?
Coaching / capability lesson
Customer communication lesson
Final closure rationale

## Lists & Settings
LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS | LISTS & SETTINGS
Status | Priority | RAG | Verification | Yes/No | Cause Type | Approval | Guidance
Not Started | Critical | Red | Not Tested | Yes | Occurrence | Draft | Yellow cells are user inputs; blue/gray cells are calculated or instructional.
In Progress | High | Amber | Planned | No | Escape | Under Review | Dates use ISO display (yyyy-mm-dd).
Blocked | Medium | Green | Verified |  | Systemic | Approved | Enter facts and evidence; avoid conclusions in the problem statement.
Complete | Low |  | Rejected |  | Direct | Rejected | No macros are used. Formulas and validation remain auditable.
Cancelled |  |  |  |  | Contributing |  | Update PFMEA, Control Plan and work instructions when the verified cause affects risk controls.